## Task Group Decision List
Speed Limit Review Requests & Decisions
| Parish | Location | Request | Date Considered by Task Group | Resolution | Date of Individual Decision for SLR | Progress to Statutory Consultation | Current Status | Date Implemented
2013 Speed Limit Review | [6 empty] | yes
| Chieveley | Priors Court Road | 40mph | 2014-03-07 | Not to introduce a lower limit and to investigate possible measures for S106 contributions made by the School. |  | No | - | -
| Chieveley | High Street | 20mph | 2014-03-07 | That a 20mph speed limit is not appropriate for Chieveley village. |  | No | - | -
| East Ilsley | Cow Lane / Compton Road | extension to 30mph | 2014-03-07 | That the existing 30mph speed limit should not be extended and that a 40mph buffer should not be introduced. |  | No | - | -
| Newbury | Old Newtown Road | 20mph outside school | 2014-03-07 | That no further action be taken until the trial on advisory 20mph speed limits outside schools is completed. |  | No | - | -
| Hungerford | Strongrove Hill |  | 2014-03-07 | That no further action is taken as the access road leading to the properties is located approximately 100 metres within the 40mph speed limit there is no road safety reason for the speed limit to be extended. |  | No | - | -
| Greenham | Bishop Green Road | 30mph | 2013-05-01 | All agreed with the recommendation that the speed limit is not changed as it is consistent with the 40mph within Hampshire. |  | No | - | -
| Newbury | Hambridge Road, Mill Lane & Boundary Road | 20mph | 2013-05-01 | It was recommended that physical measures be investigated for Hambridge Road to reduce traffic speeds. Meeting on 7 March 2014 - Given that Hambridge Road is not suitable for a 20mph speed limit it was agreed to introduce a 20mph speed limit for Mill Lane, Boundary Road and part of Kings Road |  | yes | programmed for 2014/15
| Aldermaston | Frouds Lane | (refer to last review) | 2013-05-01 | All agreed that the existing speed limit is appropriate and that pedestrian in the road signs are installed. |  | No | - | -
| Aldermaston | A340 south of village | extension to 30mph | 2013-05-01 | All agreed with the recommendation in the report that the speed limit be extended to the north of the village to include the new entrance to the residential development. It was also recommended that the speed limit be extended to the south of the village to improve visibility to the start of the 30mph speed limit. |  | yes | programmed for 2014/15
| Aldermaston | Reading Road (north of Welshman Crossroads) | lower limit | 2013-05-01 | All agreed with the recommendation in the report not to alter the speed limit as the speed and volume data indicates that there is little abuse of the current 50 mph speed limit and the accident data would tend to show that the current speed limit is appropriate for this location. |  | No | - | -
| Compton | The Downs School | introduction of 30mph | 2013-05-01 | It was agreed not to introduce a 30mph speed limit but to: • Investigate additional signs (school warning signs) and to check the exit from the car park. • Get further traffic data , • Include in Traffic Management Assessment programme for possible measures and liaise with Cllr von Celsing, Alison Strong and Lisa Hill. |  | No | - | -
| Chieveley | Graces Lane, Chieveley | Updating speed limit TRO | 2013-05-01 | Discrepancies in TRO and signing identified and requires correcting. |  | yes | completed | 2013-07-22
| Burghfield | Goring Lane, Burghfield | Updating speed limit TRO | 2013-05-01 | Discrepancies in TRO and signing identified and requires correcting. |  | yes | programmed for 2014/15
| Kintbury | Kintbury 20mph | Updating speed limit TRO | 2013-05-01 | Discrepancies in TRO and signing identified and requires correcting. |  | yes | completed | 2013-07-22
| Burghfield | Burghfield Bridge | extension to 30mph | 2013-05-01 | It was agreed that the speed limit be extended a short distance to encourage drivers to reduce their speeds prior to entering the bends. |  | yes | completed | 2014-03-04
| Thatcham | Turnpike Road | extension of 30mph | 2013-05-01 | All agreed with the recommendation to relocate the 30mph terminal sign so that it can be easily seen and due to the close proximity of the hospital junction that this be included in the extension. |  | yes | Statutory Consultation closed 13 March 2014
| Mortimer | Mortimer Lane | Investigate at officers request (terry) | 2013-05-01 | All agreed with the recommendation in the report that the existing speed limit is appropriate for a road of this nature. |  | No | - | -
2012 Speed Limit Review | [6 empty] | yes
| Speen | B4000 between A4 and Stockcross Village. | 50mph and extending 30mph towards Wickham | 2012-08-01 | 30mph section – All agreed not to extend the speed limit and undertake a feasibility design for a build out and if appropriate use S106 funding. National speed limit section – All agreed not to reduce the speed limit but consider reducing traffic speeds by using road markings. |  | no | -
| Compton | Aldworth Road | 30mph east of railway bridge | 2012-08-01 | All agreed to extend the 30mph speed limit to a location east of the church and investigate if any improvements can be made to the crossroads signs. |  | yes | to be installed March 2014 (delayed due to flooding)
| Compton | Ilsley Road | 40mph speed limit | 2012-08-01 | All agreed not to introduce a lower limit but install marker posts and assist the resident with their signs. Also consider changing the tractor sign to inform drivers of turning traffic. |  | no | -
| Welford | Half Way | Lower speed limit | 2012-08-01 | Agreed to leave at national speed limit. |  | no | -
| Aldermaston | Frouds Lane | lower speed limit | 2012-08-01 | All agreed to review Frouds Lane again when traffic data has been carried out when it is not being used as a diversion route. A traffic management assessment to be carried out following the request for traffic calming measures. |  | no | -
2011 Speed Limit Review | [6 empty] | yes
| Chieveley, Beedon | Old Oxford Road | Request for lower Limit | 2012-01-01 | All agreed for a 40mph limit to replace the existing 50mph and the length of existing national speed limit is appropriate. | 2012-02-23 | yes | completed | 2012-07-20
| Burghfield | Clay Hill Road | Petition for 40mph | 2012-01-01 | All agreed to the introduction of a 40mph limit. | 2012-02-23 | yes | completed | 2012-10-22
| Purley | Purley Village & Purley lane | 20mph speed limit | 2012-01-01 | All agreed to the introduction of a 20mph | 2012-02-23 | yes | completed | 2012-10-29
| Farnborough, Brightwalton & Leckhampstead | B4494 – between the district boundary to Egypt crossroads | review of speed limit | 2012-01-01 | Agreed that AD will start with speed reduction posters at Brightwalton Holt and then other speed reduction measures | 2012-02-23 | No | poster campaign carried out. | -
| Thatcham | Thornford Road | Lower limit | 2012-01-01 | Agreed to leave at national speed limit. | 2012-02-23 | No | -
| Tilehurst | Hildens Drive | 20mph | 2012-01-01 | All agreed to leave the speed limit at 30mph | 2012-02-23 | No | -
| Chieveley | Priors Court Road | lower limit. | 2012-01-01 | Agreed to leave at national speed limit | 2012-02-23 | No | -
| Bucklebury | Manor Farm Road, Hillfoot | Extension of 30mph | 2012-01-01 | All agreed with the recommendation that the existing 30mph speed limit be extended to include the properties | 2012-02-23 | yes | completed | 2013-06-07
| Aldermaston | Soke Road | 40mph | 2012-01-01 | All agreed to the extension of a 40mph speed limit to the Easter Park roundabout. | 2012-02-23 | yes | completed | 2012-07-20
| Wokefield | Goring Lane | lower speed limit | 2012-01-01 | All agreed with recommendation that given the high number of accidents that this length of road be included in 2012/13 local safety scheme for further investigation | 2012-02-23 | No | -
| Enborne | Outside Enborne Primary School | lower speed limit | 2012-01-01 | It was agreed that a 30mph speed limit be introduced outside the school and to include the properties on Church Lane. | 2012-02-23 | yes | completed | 2012-10-15
| Inkpen | Kintbury Road | Extend current 30mph speed limit North towards Kintbury (see SLR July 2007) | 2011-08-01 | All agreed to the recommendation to extend the 30mph speed limit and investigate if edge of carriageway road markings can be introduced to highlight where the road narrows. | 2011-08-03 | yes | speed limit introduced | 2012-03-21
| Beenham | Webbs Lane | Extension of 30mph speed limit | 2011-08-01 | Not to introduce a speed limit at this time but to erect temporary posters and undertake additional surveys including Speedwatch. Report findings to the next meeting to the Task Group. | 2011-08-03 | No | - | -
1 | Theale | Englefield Road | Review of speed limits | 2011-08-01 | All agreed that the road should be monitored following the introduction of the narrowing recommended in TMA 139. | 2011-08-03 | no | Works programmed for February 2012 school Holiday. | -
1 | Theale | The Green, Church Street | Review of speed limits | 2011-08-01 | All agreed that the speed limits are appropriate and to investigate if the zebra crossing by the primary school can be narrowed. | 2011-08-03 | no |  | -
1 | Pangbourne | Pangbourne Hill to junction with Upper Basildon | Review of speed limit. | 2011-08-01 | All agreed that the existing speed limit was appropriate but the location of the 30mph be checked in relation to the TRO. Temporary road safety posters be introduced on Pangbourne Hill and improvements to the Upper Basildon junction be investigated. | 2011-08-03 | no | TMA programmed for 2012/13 | -
| Tidmarsh & Sulham | Sulham Lane , Mill Lane & Sulham Hill. | 30mph speed limit through village | 2011-08-01 | All agreed with the recommendation to introduce a 30mph speed limit. | 2011-08-03 | yes | speed limit introduced | 2012-03-20
1 | West Ilsley | All approaches to village | extension of 30mph speed limit | 2011-08-01 | All agreed that the extents of the existing speed limits are appropriate and that no changes are recommended. Why white gates have not been introduced from the East Ilsley direction are to be investigated. | 2011-08-03 | no | Signing improvements in Eastbury programmed before end march 2012. | -
1 | Pangbourne | Road outside St Andrew's School | lower speed limit | 2011-08-01 | All agreed that the speed limits are appropriate and that measures be investigated to improve safety when improvements to the junctions on the Pangbourne to Yattendon Road are designed. | 2011-08-03 | no | - | -
| Welford | Easton | 40mph speed limit | 2011-08-01 | All agreed to the introduction of a 40mph speed limit. | 2011-08-03 | yes | speed limit introduced | 2012-03-23
1 | Brimpton | Brimpton Village to Brimpton crossroads | Request for lower limit. | 2011-08-01 | All agreed wit the recommendation that the existing speed limits are appropriate and that signing improvements for the bridge and bends be investigated. | 2011-08-03 | no | - | -
1 | Newbury | Mill Lane | 20mph speed limit | 2011-08-01 | All agreed with the recommendation not to introduce a 20mph speed limit at this time but monitor Mill Lane following the introduction of the 7.5T weight restriction. | 2011-08-03 | no | Weight restriction to be introduced | -
2010 Speed Limit Review | [6 empty] | yes
1 | Thatcham | Paynesdown Road | request for a 20mph speed limit | 2010-12-01 | It was agreed that a 20mph zone be approved in principle subject to support from a public consultation and their being sufficient funding being available to implement any necessary measures. | 2010-12-01 | no | No further action following responses to consultation and ID report. | -
1 | Thatcham | Derwent Road | request for a 20mph speed limit | 2010-12-01 | It is recommended that a 20mph speed limit be introduced by signing only. | 2010-12-01 | yes | speed limit introduced | 2012-03-23
| Thatcham | Pound Lane | request for a 20mph speed limit | 2010-12-01 | All agreed that the existing speed limit is appropriate. | 2010-12-01 | No | - | -
| Chieveley, Shaw Cum Donnington, Newbury | A339 - A34 slip road to A4 Robin Hood Roundabout | Review of A & B roads. | 2010-12-01 | All agreed with the recommendation that the existing speed limits are appropriate and therefore no change is considered necessary. | 2010-12-01 | No | - | -
1 | Newbury, Greenham | A339 - A4 Robin Hood Roundabout to Swan Roundabout | Review of A & B roads. | 2010-12-01 | Robin hood to Bear Lane roundabout - all agreed that the existing speed limit is appropriate, Bear lane to St johns roundabouts - all agreed that 40mph speed limit is appropriate, St johns to Pinchington Lane Roundabouts - all agreed that this section should remain at 50mph, Pinchington Lane to Swan roundabouts - all agreed that 50mph is appropriate but investigate signing for pedestrian crossing and investigate measures to prevent cars entering the waste site the wrong way. | 2010-12-01 | no | - | -
| Greenham | A339- Swan Roundabout o District Boundary with Hampshire | Review of A & B roads. | 2010-12-01 | All agreed that the existing 50mph speed limit is appropriate. | 2010-12-01 | No | - | -
| Newbury | A343 - District Boundary with Hampshire to Newbury | Review of A & B roads. | 2010-12-01 | All agreed that the existing speed limits are appropriate and no changes are considered necessary. | 2010-12-01 | No | - | -
| Padworth, Beenham, Sulhamstead, Ufton, Englefield, Theale | A4 - A340 roundabout at Aldermaston to A340 roundabout at Theale | From April Review | 2010-12-01 | It was agreed that a 50mph speed limit be introduced to cover its junctions with Beenham Industrial Estate and the Beenham village. The existing speed limit on the remaining length of the A4 is appropriate. | 2010-12-01 | yes | completed | 2013-01-21
| Theale | A4 - A340 roundabout at Theale to M4 junction 12 | Review of A & B roads. | 2010-12-01 | All agreed that the current 70 mph (National) speed limit is appropriate and therefore no change is considered necessary. | 2010-12-01 | No | - | -
| Calcot, Tilehurst | A4 - M4 Junction 12 to district boundary with Reading | Review of A & B roads. | 2010-12-01 | All agreed that the existing speed limits are appropriate and therefore no change is considered necessary. | 2010-12-01 | No | - | -
| Woolhampton, Beenham, Padworth | A4 - Woolhampton to A340 roundabout at Aldermaston | From April Review | 2010-12-01 | It was agreed that the 30mph speed limit be extended to the west of the Woolhampton village and the length of A4 to the east of the village remains at national speed limit. Also investigations are undertaken for a pedestrian refuge at Broom Hill. | 2010-12-01 | yes | Speed limit completed. Pedestrian refuge installed October 2013. | 2012-01-23
| Newbury | B3421 Hambridge Road - A339 Bear Lane roundabout to A4 Bath Road | Review of A & B roads. | 2010-12-01 | It was agreed that the existing speed limits are appropriate and to investigate a cycle facility on one side of the road. | 2010-12-01 | No | - | -
| Curridge, Hermitage | B4009 at Curridge | Review of A & B roads. | 2010-12-01 | All agreed that the existing speed limit is appropriate. | 2010-12-01 | No | - | -
| Newbury, Shaw Cum Donnington, Chieveley, Winterbourne | B4494 - A4 Western Avenue to Chieveley Junction | Review of A & B roads. | 2010-12-01 | All agreed that the existing speed limits are appropriate and therefore no change is considered necessary. | 2010-12-01 | No | - | -
| Leckhampstead | B4494 - Chieveley Junction to Chapel Arch Crossroads | Review of A & B roads. | 2010-12-01 | All agreed with recommendation that the existing speed limit is appropriate. | 2010-12-01 | No | - | -
| Greenham | B4640 - District Boundary with Hampshire to A339 Swan Roundabout | Review of A & B roads. | 2010-12-01 | All agreed that the existing 50mph speed limit is appropriate | 2010-12-01 | No | - | -
| Wokefield | Goring Lane, Grazeley Green | From April Review | 2010-12-01 | All agreed that as there had been no injury accidents since the measures were introduced that it continued to be monitored and the ward members be updated on progress. | 2010-12-01 | No | - | -
| Newbury | Town centre -Northcroft Lane, Strawberry Hill, Bear Lane, Market Street & Bartholomew | 20mph speed limit zone from Northcroft Lane Petition | 2010-12-01 | All agreed to the introduction of a 20mph speed limit zone. | 2010-12-01 | yes | completed | 2014-03-05
| Basildon, Streatley | A329 - Lower Basildon to Streatley | Review of A & B roads. | 2010-04-01 | All agreed with the recommendation that the current speed limits are appropriate. | 2010-05-28 | No | - | -
| Basildon | A329 - Pangbourne Parish Boundary to Lower Basildon | Review of A & B roads. | 2010-04-01 | All agreed with the recommendation that the current speed limits are appropriate. | 2010-05-28 | No | - | -
| Streatley | A329 - to district boundary with Oxfordshire | Review of A & B roads. | 2010-04-01 | All agreed with the recommendation that the current speed limits are appropriate. | 2010-05-28 | No | - | -
| Padworth, Beenham, Sulhamstead, Ufton, Englefield, Theale | A4 - A340 roundabout at Aldermaston to A340 roundabout at Theale | Review of A & B roads. | 2010-04-01 | All agreed for additional surveys to be undertaken with the results being presented to the next meeting g of the speed limit review. | 2010-05-28 | No | - | -
1 | Tidmarsh, Englefield, Theale | A340 - Parish Boundary with Pangbourne to A4 Bath Road | Review of A & B roads. | 2010-04-01 | All agreed that the 30mph speed limit in Tidmarsh and 50mph to the south of Tidmarsh are appropriate and that a 40mph speed limit be introduced for the length between Tidmarsh and Pangbourne. | 2010-05-28 | Yes | completed | 2011-01-28
1 | Midgham, Woolhampton | A4 - Colthrop Roundabout to Woolhampton | Review of A & B roads. | 2010-04-01 | All agreed with the recommendation to extend the 30mph speed limit at Woolhampton so that a gateway feature could be introduced and the visibility for traffic exiting the village hall car park be improved. | 2010-05-28 | Yes | completed | 2012-01-23
| Woolhampton, Beenham, Padworth | A4 - Woolhampton to A340 roundabout at Aldermaston | Review of A & B roads. | 2010-04-01 | It was agreed that the request by Woolhampton Parish Council be considered at the next meeting of the speed limit review. | 2010-05-28 | No | - | -
| Streatley | A417 Wantage Road | Review of A & B roads. | 2010-04-01 | All agreed with the recommendation that the current speed limits are appropriate. | 2010-05-28 | No | - | -
1 | Brimpton, Wasing, Aldermaston | B3051 - District Boundary with Hampshire to A340 Calleva Park Roundabout | Review of A & B roads. | 2010-04-01 | Following a site visit it was agreed that WBC would cut back the vegetation at Highfield House and adjacent to Audley House, traffic surveys and an assessment of build outs be undertaken. This can be discussed with the local member with an update being given at the next task group meeting. | 2010-05-28 | No | Update reported to December review. | -
| Lambourn, | B4000 - Lambourn Village to District Boundary with Wiltshire | Review of A & B roads. | 2010-04-01 | All agreed with the recommendation that the current speed limits are appropriate. | 2010-05-28 | No | - | -
| Lambourn, | B4000 - Woodlands St Mary's to Lambourn Village | Review of A & B roads. | 2010-04-01 | All agreed with the recommendation that the current speed limits are appropriate. | 2010-05-28 | No | - | -
| Lambourn, | B4001 - Lambourn Village to District Boundary with Oxfordshire | Review of A & B roads. | 2010-04-01 | All agreed with the recommendation that the current speed limits are appropriate. | 2010-05-28 | No | - | -
| Lambourn, | B4001 - B4000 junction to District Boundary with Wiltshire | Review of A & B roads. | 2010-04-01 | All agreed with the recommendation that the current speed limits are appropriate. | 2010-05-28 | No | - | -
1 | Streatley, Aldworth | B4009 - A329 crossroads to Aldworth | Review of A & B roads. | 2010-04-01 | All agreed with the recommendation that the existing 30mph and national speed limits are appropriate and to reduce the existing 40mph through Westridge Green to 30mph. | 2010-05-28 | Yes | completed | 2011-03-25
1 | Aldworth, Hampstead Norreys | B4009 - Aldworth to Hampstead Norreys | Review of A & B roads. | 2010-04-01 | All agree with the recommendation to introduce a 40mph speed limit from Hampstead Norreys to a location north of the bend by the Living Rain Forest. | 2010-05-28 | Yes | completed | 2011-03-25
| Streatley | B4009 - District Boundary with Oxfordshire to A329 crossroads | Review of A & B roads. | 2010-04-01 | All agreed with the recommendation that the current speed limits are appropriate. | 2010-05-28 | No | - | -
1 | Bradfield | Bradfield College | 20mph speed limit zone | 2010-04-01 | introduce a 20mph speed limit zone. | 2010-05-28 | Yes | completed | 2010-10-01
| Pangbourne | Pangbourne Road, Upper Basildon | request for lower speed limit | 2010-04-01 | All agreed with the recommendation that the current speed limits are appropriate. | 2010-05-28 | No | - | -
1 | Wokefield | Goring Lane, Grazeley Green | Request for change of 50mph to 40mph limit | 2010-04-01 | All agreed that the section of road remain at 50mph and introduce the measures listed within TMA 114 together with the investigation for the use of rumble strips and repeater signs. An update on the situation to be reported to the next meeting of the speed limit review. | 2010-05-28 | No | completed | 2010-12-01
1 | Newbury | Dorneywood way area | 20mph speed limit zone | 2010-04-01 | introduce a 20mph speed limit zone. | 2010-05-28 | Yes | completed | 2011-01-28
1 | Burghfield | Reading Road, Cunning Man to the Hollybush Lane crossroads | review of speed limit | 2010-04-01 | 1. The length of national speed limit between Burghfield Bridge and the Reading Borough boundary be reduced to 40mph. 2. The speed limit between Burghfield Bridge and Burghfield Village is reduced to 50mph. 3. All other speed limits along Reading Road are appropriate but investigate the possibility of improving or slightly re-locating the signs at the transition between the 40 and 30mph limits at the top of Hermits Hill. | 2010-05-28 | Yes | completed | 2011-02-04
2009 Speed Limit Review | [6 empty] | yes
1 | Purley, Pangbourne | A329 - District Boundary with Reading to Pangbourne Village (junction with Sulham Lane) | Review of A & B roads. | 2009-12-01 | Replace 40mph speed limit with 30mph. | 2010-02-15 | Yes | completed | 2010-08-06
1 | Fawley | A338 - Fawley Junction to District Boundary with Oxfordshire | Review of A & B roads. | 2009-12-01 | That the speed limit north of Great Shefford should be reduced to 50mph limit. | 2010-02-15 | Yes | completed | 2011-02-07
1 | Great Shefford, Fawley | A338 - M4 Junction 14 to Fawley Junction | Review of A & B roads. | 2009-12-01 | All agreed that the speed limits between the M4 and Great Shefford are appropriate and that the speed limit north of Great Shefford should be reduced to 50mph limit. | 2010-02-15 | Yes | completed | 2011-02-07
| Aldermaston, Padworth | A340 - A4 Bath Road to Aldermaston Village | Review of A & B roads. | 2009-12-01 | It was agreed that the existing speed limits are appropriate but to introduce an advisory 40mph sign at the bend to the north of the village. | 2010-02-15 | No | - | -
| Aldermaston | A340 - Aldermaston village to District boundary | Review of A & B roads. | 2009-12-01 | All agreed not to alter the existing speed limits | 2010-02-15 | No | - | -
| Upper Basildon | Aldworth Road | Extend existing 30mph | 2009-12-01 | All agreed not to alter the existing speed limits | 2010-02-15 | No | - | -
| Upper Basildon | Ashampstead Road | Extend existing 30mph | 2009-12-01 | All agreed not to alter the existing speed limits | 2010-02-15 | No | - | -
| Great Shefford, East Garston, Lambourn | B4000 - Welford Parish Boundary to Woodlands St Mary | Review of A & B roads. | 2009-12-01 | All agreed not to alter the existing speed limits. | 2010-02-15 | No | - | -
| Compton | Compton to East Ilsley Road | Request to extend 30mph limit towards East Ilsley | 2009-12-01 | It was agreed not to extend the existing speed limit, but to improve the warning signs and marker posts at the bend. | 2010-02-15 | No | - | -
1 | Ashampstead | Dog Lane, Holly Lane & Palmers Hill | Extension to 30mph | 2009-12-01 | It was agreed that the 30mph sped limit is extended on Dog Lane to the vicinity of Bridleway No 22 and on Holly Lane by approx 100m to include the frontage development to the east of Noakes Hill. That a 30mph speed limit be introduced on Noakes Hill | 2010-02-15 | Yes | completed | 2011-01-28
1 | Kintbury | Station Road, Kintbury | Request for 40mph | 2009-12-01 | Introduce 40mph speed limit to cover the priority working systems. | 2010-02-15 | Yes | completed | 2010-09-08
1 | Fawley | Village centre | Request for speed limit | 2009-12-01 | All agreed with the recommendation to implement a 30mph speed limit in both North and South Fawley villages. | 2010-02-15 | Yes | completed | 2011-02-16
1 | Welford | Welford Road - outside Primary School | Request for 30mph | 2009-12-01 | All agreed to the recommendation to introduce a 30pmh limit outside of the school and on Church Hill. | 2010-02-15 | Yes | completed | 2011-01-28
1 | Streatley | Rectory Road | Extend the existing 30mph speed limit | 2009-05-01 | All agreed with the recommendation to extend the speed limit. | 2009-06-30 | Yes | completed | 2010-02-26
1 | Newbury | Queens Road | 20mph speed limit zone | 2009-05-01 | All agreed with the recommendation to implement a 20mph speed limit on Queens Road, its adjacent roads and to include Boundary Road. | 2009-06-30 | Yes | completed | 2010-11-24
| Ufton Nervet | Ufton Lane | Request for a 30mph Speed limit | 2009-05-01 | All agreed that no change should be made to the existing speed limit on this stretch of road. | 2009-06-30 | No | - | -
1 | Stratfield Mortimer | The Avenue | Request for lower speed limit | 2009-05-01 | It was agreed that a 20mph speed limit with repeater signs be introduced. | 2009-06-30 | Yes | completed | 2010-08-18
1 | Stanford Dingley | Stanford Dingley Village | Request for a 30mph Speed limit | 2009-05-01 | All agreed with the recommendation that a 30mph speed limit be introduced to the village. | 2009-06-30 | Yes | completed | 2010-06-01
| Kintbury | A4 - Parish Boundary to Half way | Review of A & B roads. | 2009-05-01 | All agreed with the recommendation that the national speed limit is appropriate. | 2009-06-30 | No | - | -
| Speen / Welford | A4 - Halfway to A34/B4000 roundabouts | Review of A & B roads. | 2009-05-01 | All agreed with the recommendation that the national speed limit is appropriate. | 2009-06-30 | No | - | -
| Speen / Boxford | B4000 - A4 / A34 Roundabout at Speen to Wickham Heath | Review of A & B roads. | 2009-05-01 | All agreed with the recommendation that the existing speed limits are appropriate. | 2009-06-30 | No | - | -
| Speen | Bagnor village | Request for lower speed limit | 2009-05-01 | Following the task group site visit to Bagnor Village, the decision was made not to introduce a speed limit. | 2009-06-30 | No | - | -
1 | Boxford /Welford | B4000 - Wickham Heath to Welford Parish Boundary | Review of A & B roads. | 2009-05-01 | All agreed with the recommendation to relocate the start of the 40mph speed limit to the south of Wickham village further south. | 2009-06-30 | Yes | completed | 2011-01-28
1 | Hermitage | Yattendon Road | review of 30mph speed limit | 2009-05-01 | It was agreed that the sign should be re-positioned so that it is more visible. | 2009-06-30 | Yes | completed | 2010-01-22
1 | Hamstead Norreys / Hermitage | B4009 - Hampstead Norreys to Hermitage | Review of A & B roads. | 2009-05-01 | All agreed that the start of the 30mph at Hermitage be extended to the location of the white gates. It was also agreed that the rest of the speed limits are appropriate and that an assessment of signing prior to the bridge at Hampstead Norreys be undertaken. | 2009-06-30 | Yes | completed | 2010-01-22
2008 Speed Limit Review | [6 empty] | yes
1 | Greenham | Greenham Road and Burys Bank Road | Reduce 40mph limit to 30mph | 2008-11-01 | All agreed with recommendation within the report to introduce a 30mph speed limit. | 2009-02-13 | Yes | completed | 2009-07-03
1 | Shaw Cum Donnington | B4009 Long Lane | Review of A & B roads. | 2008-11-01 | All agreed with recommendation within the report that the 30mph at Long Lane is extended south to include the entrance to Mousefield Farm and that the start of the 30mph is extended south of Curridge prior to the bends. | 2009-02-13 | Yes | completed | 2010-01-22
| Brimpton | Brimpton Road (from Crookham Hill) | review of speed limit | 2008-11-01 | It was agreed that the existing speed limit is appropriate. | 2009-02-13 | No | - | -
1 | Beech Hill | Beech Hill Road | Request for extension to 30mph speed limit | 2008-11-01 | All agreed with recommendation to extend the 30mph by approximately 75 metres. | 2009-02-13 | Yes | completed | 2009-07-31
| East Garston | Newbury Road | Reduce 40mph limit to 30mph | 2008-11-01 | It was recommended to introduce a 30mph speed limit and that safety measures are introduced as part of next years capital programme. | 2009-02-13 | No | - | -
1 | Hungerford | Hungerford Common | Introduction of 30mph | 2008-11-01 | It was agreed that authorisation be sought for introducing a speed limit through the Common without the need for repeater signs. | 2009-02-13 | Yes | GOSE did not approve application. Agreed to implement 30mph with repeater signs. Completed. | 2010-10-15
1 | Hungerford | Upper Eddington | extension of 30mph | 2008-11-01 | All agreed with recommendation within the report to introduce a 30mph speed limit. | 2009-02-13 | Yes | completed | 2009-08-21
1 | Hungerford | Charnham Park | Reduce 40mph limit to 30mph | 2008-11-01 | All agreed to extend the 30mph speed limit from the roundabout to include the first junction into the housing estate. | 2009-02-13 | Yes | completed | 2009-08-21
| Hungerford | A338 between M4 and A4 Bath Road | Review of A & B roads. | 2008-11-01 | All agreed with recommendation within the report that the existing speed limits are appropriate. | 2009-02-13 | No | - | -
| Hungerford | A338 between A4 Bath Road and District Boundary | Review of A & B roads. | 2008-11-01 | All agreed with recommendation within the report that the existing speed limits are appropriate. | 2009-02-13 | No | - | -
| Hungerford | A4 between Town Council boundary (east) and A338 | Review of A & B roads. | 2008-11-01 | All agreed with recommendation within the report that the existing speed limits are appropriate. | 2009-02-13 | No | - | -
| Hungerford | A4 between A338 and B4192 | Review of A & B roads. | 2008-11-01 | All agreed with recommendation within the report that the existing speed limits are appropriate. | 2009-02-13 | No | - | -
| Hungerford | A4 between B4192 and District boundary | Review of A & B roads. | 2008-11-01 | All agreed with recommendation within the report that the existing speed limits are appropriate. | 2009-02-13 | No | - | -
| Hungerford | B4192 between A4 and District boundary | Review of A & B roads. | 2008-11-01 | All agreed with recommendation within the report that the existing speed limits are appropriate. | 2009-02-13 | No | - | -
| Newbury | A4 between Lower Way and Robin Hood Roundabout | Review of A & B roads | 2008-11-01 | All agreed with recommendation within the report that the existing 40mph speed limit is appropriate. | 2009-02-13 | No | - | -
| Chieveley | Priors Court Road | Assessment of road | 2008-11-01 | it was agreed that the existing speed limit is appropriate and any safety issues at the school entrance can be dealt with separately. | 2009-02-13 | No | - | -
1 | Pangbourne | A 340 from Pangbourne through to Tidmarsh | Review of A & B roads | 2008-04-01 | All agreed with the recommendation to extend the existing 30mph speed limit to include its junction with Flowers Hill. | 2008-06-30 | Yes | completed | 2009-01-30
| Pangbourne | A239 High street / Reading Road | Review of A & B roads | 2008-04-01 | It was considered that the existing 30mph was appropriate and therefore all agreed with recommendation not to amend the speed limits. | 2008-06-30 | No | - | -
| Pangbourne | A329 Shooters Hill | Review of A & B roads | 2008-04-01 | It was considered that the existing 30mph was appropriate and therefore all agreed with recommendation not to amend the speed limits. | 2008-06-30 | No | - | -
1 | Pangbourne | Village centre | 20mph Zone following traffic study | 2008-04-01 | All agreed that a 20mph speed limit zone be introduced with the extents being agreed with the Parish Council and the Police. | 2008-06-30 | Yes | completed | 2009-10-30
| Pangbourne | B471 - A329 to district boundary | Review of A & B roads | 2008-04-01 | All agreed with recommendation not to amend the speed limit on this length of road. | 2008-06-30 | No | - | -
1 | Burghfield | Clay Hill Road | request for a lower speed limit | 2008-04-01 | All agreed with recommendation to introduce a 50mph speed limit on this length of road. | 2008-06-30 | Yes | completed | 2009-02-28
1 | Lambourn | Baydon Road | discrepancy in TRO and speed limit | 2008-04-01 | All agreed to amend the TRO to match the existing speed limit signs. | 2008-06-30 | Yes | completed | 2009-03-12
| Chieveley | Priors Court Road | request for a lower speed limit | 2008-04-01 | It was recommended that this section of road be reconsidered in October 2008 with up to date traffic surveys and recorded injury accidents. | 2008-06-30 | No | - | -
| Speen | Lambourn Road | discrepancy in TRO and speed limit | 2008-04-01 | All agreed that the speed limit be amended to the location of the TRO. | 2008-06-30 | No | - | -
1 | Thatcham | Crookham Hill | request for a lower speed limit | 2008-04-01 | It was recommended to introduce a 40mph speed limit on Crookham Hill and to include its junction with Thornford Road. | 2008-06-30 | Yes | completed | 2009-09-18
1 | Beenham | Beenham Hill | Request for a 30mph Speed Limit. | 2008-04-01 | All agreed to introduce a 30mph speed limit. | 2008-06-30 | Yes | completed | 2009-03-20
2007 Speed Limit Review - New Speed Limit Assessment Criteria used from this point forward | [6 empty] | yes
| Newbury | A4 between Robin Hood and A34/B4000 Roundabouts | Review of A & B roads | 2007-11-27 | It was recommended that the speed limit should be not altered but to inform members of proposed measures on this length of road. | 2007-12-21 | No | - | -
| Newbury | A4 between Lower Way and Robin Hood Roundabout | Review of A & B roads | 2007-11-27 | It was recommended that this section of road be reconsidered in April 2008 with up to date traffic surveys and recorded injury accidents. | 2007-12-21 | No | - | -
| Thatcham | A4 between Henwick Lane and Lower way | Review of A & B roads | 2007-11-27 | All agreed that the 40mph remain as existing and that consideration be given to the introduction of a speed camera. | 2007-12-21 | No | - | -
| Thatcham | A4 between Falmouth Way Roundabout and Henwick Lane | Review of A & B roads | 2007-11-27 | All agreed to with recommendation not to amend the speed limits on this length of road. | 2007-12-21 | No | - | -
| Thatcham | A4 between Colthrop and Falmouth Way Roundabout | Review of A & B roads | 2007-11-27 | All agreed to with recommendation not to amend the speed limits on this length of road. | 2007-12-21 | No | - | -
| Wokefield | Goodboys Lane | 30mph (Petition reported to KPAF on 18 July 2007 | 2007-11-27 | All agreed not to introduce a 30mph speed limit, but to investigate the current road signing particularly at the approach to the residential properties and Goring Lane. | 2007-12-21 | No | - | -
1 | Beech Hill | Bloomfield Hatch Lane | Extend existing 40mph speed limit from Lambs Hill to Alfreys Bridge. | 2007-11-27 | All agreed to introduce a 40mph speed limit to Alfreys Bridge. | 2007-12-21 | Yes | completed | 2008-10-03
1 | Pangbourne | Flowers Hill Courtlands Hill | Consider implementation of 30 mph speed limit. | 2007-11-27 | All agreed to introduce a 30mph speed limit. | 2007-12-21 | Yes | completed | 2009-01-30
1 | Bucklebury & Thatcham North | Harts Hill Road | Due to the high occurrence of crashes review the current National Speed Limit | 2007-11-27 | All agreed to introduce a 40mph speed limit from Floral Way to Upper Bucklebury with max speed advisory signs at the bend. | 2007-12-21 | Yes | completed | 2008-11-14
| Newbury | Fir Tree Lane | 20mph outside school | 2007-07-31 | Not to introduce a 20 mph speed limit at this time but to check S106 funds and then look at a favourable design with the school and the ward members. | 2007-09-25 | No | - | -
1 | Upper Lambourn | High Street and adjoining roads. | National speed limit to be reviewed. | 2007-07-31 | All agreed to introduce a 30mph speed limit. | 2007-09-25 | Yes | completed | 2008-03-28
1 | Thatcham | Various roads | Renew 20mph limit | 2007-07-31 | All agreed to that the 20mph speed limit should be made permanent.. | 2007-09-25 | Yes | completed | 2008-03-28
| Hamstead Marshall | Main Road through village | Extend the 30mph speed limit | 2007-07-31 | Agreed with recommendation to extend the 30mph speed limit and that ‘gateway features are introduced | 2007-09-25 | yes | completed | 2008-03-25
1 | Aldermaston | Church Road | Extend existing 30 mph limit to beyond the Church | 2007-07-31 | All agreed to extend the 30mph speed limit to a location beyond the Church and for a gateway feature to be introduced. | 2007-09-25 | Yes | completed | 2007-12-21
| Lilley | B 4494 from lilley to the South Oxfordshire border | Review of A & B roads | 2007-07-31 | All agreed that a speed limit should not be introduced. | 2007-09-25 | No | - | -
| Inkpen | Kintbury Road | Extend current 30mph speed limit North towards Kintbury vicinity of 'Fairfields' | 2007-07-31 | Not to extend the 30mph speed limit. | 2007-09-25 | No | - | -
| Bucklebury | Harts Hill Road | Due to the high occurrence of crashes review the current National Speed Limit | 2007-07-31 | to be reassess as not all Cllrs invited to review | 2007-09-25 | No | - | -
1 | Brightwalton Green | Brightwalton Green Village | Request for a 30mph Speed Limit. | 2007-07-31 | All agreed to introduce a 30mph speed limit. | 2007-09-25 | Yes | completed | 2008-03-28
1 | Eastbury | Newbury Road | Extend the existing 30 mph speed limit at each end of the village. | 2007-07-31 | All agreed to extend the existing 30mph speed limit to include the new frontages | 2007-09-25 | Yes | completed | 2008-04-14
| Leckhampstead | B 4494 Leckhampstead | Review of A & B roads | 2007-07-31 | All agreed that a speed limit should not be introduced. | 2007-09-25 | No | - | -
2006 Speed Limit Review | [6 empty] | yes
| Boxford | Rood Hill | 40mph limit | 2006-10-23 | All agreed that a 40mph speed limit should be introduced. | 2006-12-21 | Yes | completed
| Burghfield | Hangar Road, Sheffield Bottom | introduction of 30mph | 2006-10-23 | Seek legal advice regarding the installation of street lights with no Speed Limit TRO and investigate improved signing on the approaches to the swing bridge. | 2006-12-21 | No | - | -
1 | Burghfield/Wokefield | Goring Lane | extension of 30mph | 2006-10-23 | Extend the existing 30mph speed limit to include the rear entrance to the residential properties. | 2006-12-21 | Yes | completed | 2007-07-20
| Beenham | Beenham Hill | extension to 30mph | 2006-10-23 | Not to introduce 30mph speed limit but create a gateway with the existing 40mph speed limit. Decision overturned by Exec Member at Individual Decision and 30mph to be extended. | 2006-12-21 | No | - | -
1 | Theale | Waterside Drive | 30 mph | 2006-10-23 | Introduce 30mph speed limit. | 2006-12-21 | Yes | completed | 2008-11-07
| Kintbury | Kintbury Village | 20mph | 2006-10-23 | Not to introduce a 20mph speed limit zone at this time but to investigate various measures for Kintbury in consultation with the Ward Member and Parish Council to address the Parish Council concerns. | 2006-12-21 | No | - | -
| Chieveley | B4494 Snelsmore Common | Introduction of 50mph | 2006-10-23 | Not to introduce the 50mph speed limit at this time but to review it in October 2007 in accordance with the new speed limit criteria. Signing improvements to be undertaken at Snelsmore Common Car Park with advisory speed signs being introduced at Bussocks Hill. | 2006-12-21 | No | - | -
1 | Theale | High Street | Introduction of 20mph | 2006-10-23 | Introduce 20mph speed limit zone. | 2006-12-21 | Yes | completed | 2008-02-01
| Bucklebury | Manor Farm Road, Hillfoot | Extension of 30mph | 2006-10-23 | Not to extend the existing speed limit and investigate improved signing. | 2006-12-21 | No | - | -
| Enborne | Church Farm, Enbourne | introduction of 30mph | 2006-10-23 | Not to introduce a speed limit but investigate signing improvements at Church Farm. | 2006-12-21 | No | - | -
| Brimpton | B3051 Brimpton Common | introduction of 30mph | 2006-10-23 | Not to change the speed limit at this time but review it before 2011 in line with the new speed limit assessment criteria and to investigate the accidents at the crossroads to determine if any safety improvements can be introduced. | 2006-12-21 | No | - | -
1 | Streatley | A329 Reading Road | Extension to 30mph | 2006-10-23 | Extend the existing 30mph speed limit to include the new frontages. | 2006-12-21 | Yes | completed | 2008-01-25
1 | Newbury | A339 Mill Lane To Greenham Road Roundabouts | increase existing 30mph to 40mph | 2006-03-17 | All agreed with recommendation to increase to 40mph as it makes sense and is appropriate. | 2006-05-23 | Yes | completed
1 | Newbury | A343 Sandpit Hill, Wash Water | introduce 50mph | 2006-03-17 | All agreed to recommendation for a 50mph to be introduced | 2006-05-23 | Yes | completed | 2007-09-05
| Compton | Unnamed Road at Downs School | reduce to 30mph | 2006-03-17 | Site visit to Compton with Barbara Alexander and Downs School Head Teacher in attendance. All agreed to keep 40mph speed limit but to extend it further south and improve signing (speed limit count down markers if possible). Vehicle speeds to be monitored after these measures have been introduced | 2006-05-23 | No | - | -
| Shaw | B4009 Shaw (New Mousefield Farm entrance). | extend existing 30mph | 2006-03-17 | All agreed with recommendation and not to extend speed limit. | 2006-05-23 | No | - | -
| Hermitage | B4009 Rookery Farm | extend existing 30mph | 2006-03-17 | All agreed with recommendation and not to extend speed limit. | 2006-05-23 | No | - | -
1 | Greenham | A339 Greenham Common | introduce 50mph | 2006-03-17 | All agreed to recommendation for a 50mph to be introduced | 2006-05-23 | Yes | completed
| Purley on Thames | A329 Oxford Road & Purley Rise | reduce to 30mph | 2006-03-17 | All agreed with recommendation not to reduce speed limit and to monitor traffic speeds after the remedial measures have been introduced. | 2006-05-23 | No | - | -
1 | Aldworth | Ashampstead Road | extend existing 40mph | 2006-03-17 | Agreed with recommendation to extend existing 40mph to include the frontage development. | 2006-05-23 | Yes | completed
| Tidmarsh | A340 Pangbourne Road | extend existing 30mph | 2006-03-17 | All agreed to keep 30mph at existing location, but investigate count down markers and signs. | 2006-05-23 | No | - | -
| Sulham | Sulham Lane | introduction of 30mph | 2006-03-17 | All agreed not to introduce a speed limit, but to investigate the introduction of warning signs to reduce speeds (measures could include warning sign for Horses, pedestrians in road and coloured surfacing, slow marking and anti skid at Sulham Hill Junction). | 2006-05-23 | No | - | -
1 | Mortimer | The Street | reduce existing 40mph to 30mph | 2006-03-17 | agreed with recommendation to introduce 30mph | 2006-05-23 | Yes | completed
1 | Aldermaston | Chapel Lane | introduce 30mph | 2006-03-17 | All agreed with recommendation to introduce 30mph. | 2006-05-23 | Yes | completed | 2007-12-21
1 | Aldermaston | Padworth Common Road | introduce 50mph | 2006-03-17 | All agreed with recommendation to introduce 50mph. | 2006-05-23 | Yes | completed | 2007-12-21
1 | Aldermaston | Red Lane | extend existing 40mph | 2006-03-17 | All agreed with recommendation to extend 50mph | 2006-05-23 | Yes | completed | 2007-12-21
1 | Aldermaston | Welshmans Road | extend existing 50mph | 2006-03-17 | All agreed with recommendation to extend 50mph and work with Hampshire County Council to extend the speed limit further to cover the frontage development. | 2006-05-23 | Yes | completed | 2007-12-21
1 | Hampstead Norreys | Compton Road | reduce existing 40mph to 30mph | 2006-03-17 | All agreed with recommendation to introduce 30mph. | 2006-05-23 | Yes | completed | 2007-03-12
| Aldermaston | A340 Calleva Park roundabout to Mullford Hill | introduce 40mph | 2006-03-17 | All agreed with recommendation to introduce 40mph | 2006-05-23 | Yes | completed
2005 Speed Limit Review | [6 empty] | yes
| Newbury | Westfields, Newbury | Introduce TRO to support 20mph speed limit currently signed on street | 2005-08-24 | All agreed to make the 20mph speed limit permanent | 2005-10-18 | Yes | completed
| Chieveley | Priors Court Road | Request for extension to 30mph speed limit | 2005-08-24 | All agreed to the introduction of a 40mph buffer and that improved signing of the junction and bend by the nursery school be investigated. | 2005-10-18 | Yes | completed
| Cold Ash | Cold Ash Hill | Request for change of 40mph to 30mph limit | 2005-08-24 | It was agreed that the introduction of a 30mph could increase traffic speeds on the adjacent 30mph speed limits and the existing 30mph will loose their impact. It was also considered that the existing 40mph buffer gave the impression to drivers that they are leaving Thatcham and entering Cold Ash. It was agreed that the existing 40mph speed limit remain. | 2005-10-18 | No | - | -
| Compton | Unnamed Road at Downs School | Request for change of 40mph to 30mph limit | 2005-08-24 | There was some discussion about the changing and extending of the speed limit, but it was agreed that the situation be deferred until the development of the school is completed so a better assessment can be made. | 2005-10-18 | No | - | -
| Farnborough | Copperage Road | Request for extension to 30mph speed limit | 2005-08-24 | All agreed that the existing 30mph speed limit should be extended to commence at the village name plate. | 2005-10-18 | Yes | completed
| Thatcham | Bowling Green Road | Request for extension to 30mph speed limit | 2005-08-24 | All agreed that the speed limit should be extended to cover the junction. | 2005-10-18 | Yes | completed
| Thatcham | A4 Benham Hill. | Request for change of 40mph to 30mph limit | 2005-08-24 | It was agreed that this should be considered as part of the A4 Study. However it was agreed that the start of the 30mph speed limit at Henwick Lane should be located further west of the junction to improve visibility of the speed limit signs. | 2005-10-18 | Yes | completed
| Lambourn | B4000 Woodlands St Mary | Request for 40mph speed limit | 2005-08-24 | All agreed that a 40mph would not be appropriate for this length of road and that the effectiveness of the recent 50mph and safety measures need to be determined before further consideration of any speed limits on this length of road. | 2005-10-18 | No | - | -
| Wickham | B4000, Wickham | Request for extension to 40mph speed limit | 2005-08-24 | It was considered that extending the 40mph could have a detrimental effect on traffic speed through Wickham. It was therefore agreed not to extend the existing 40mph speed limit | 2005-10-18 | No | - | -
| Leckhampstead | Leckhampstead Thicket | Request for 30mph speed limit | 2005-08-24 | Given that the criteria for a 30mph speed limit is met it is recommended that a 30mph speed limit be introduced. | 2005-10-18 | Yes | completed
| Leckhampstead | Leckhampstead Village | Request for extension to 30mph speed limit | 2005-08-24 | Recommend to extend the existing 30mph speed limit to the south so that it starts at the junction. | 2005-10-18 | Yes | completed
| Newbury | Wash Water, Newbury | Request for extension to 30mph speed limit | 2005-08-24 | Recommend to extend the 30mph speed limit to the east of the entrance to the development. It was also agreed that the length of road from the recommended speed limit to the A343 Andover Road should be considered as part of the speed limit review for the A343 Sandpit Hill, to be reviewed during 2006. | 2005-10-18 | Yes | completed
| Purley on Thames | A329 Oxford Road & Purley Rise, | Request for change of 40mph to 30mph limit | 2005-08-24 | It was agreed that a 30mph speed limit would be inappropriate for this length of road and that the 40mph should remain. It was also agreed that the accidents should be investigated. | 2005-10-18 | No | - | -
| Chieveley | B4494, Snelsmore Common | Request for 50mph speed limit | 2005-08-24 | After careful consideration and a site visit it was agreed not to introduce a 50mph but investigate improvements to the signing, especially for the entrances to the School and Snelsmore Common. | 2005-10-18 | No | - | -
| Burghfield | Goring Lane, Grazeley Green | Request for change of 50mph to 40mph limit | 2005-08-24 | Given the results of the traffic survey and that there have been no recorded accidents since the 50mph was introduced during October 2003, it was agreed that the current 50mph speed limit is appropriate. | 2005-10-18 | No | - | -
| Theale | Station Road, Theale | Officers recommendation to extend 30mph speed limit to cover the railway bridge and the pedestrian access to the platforms. | 2005-08-24 | All were in agreement to the extension of the 30mph speed limit to a point south of Arrowhead Road. | 2005-10-18 | Yes | completed
| West Illsley | West Ilsley Village | Request to extend 30mph speed limits on village approaches | 2005-08-24 | Recommend to extend the 30mph to the north of the village and that the start of the 30mph south of the village is appropriate | 2005-10-18 | Yes | completed
| Great Shefford | A338 Wantage Road, Great Shefford | Request to extend 30mph speed limit on village approach | 2005-08-24 | Given that there was no change in the situation since it was considered by the Task Group during 2004, all agreed with the recommendation of the report that the current speed limit is appropriate. | 2005-10-18 | No | - | -
| Great Shefford | A338 between the M4 and Great Shefford | Request for 50mph speed limit | 2005-08-24 | There was a discussion about this speed limit and it was agreed not to introduce a 50mph speed limit at the present time but for it to be considered as part of the A338 road safety study. | 2005-10-18 | No | - | -
2004 Speed Limit Review | [6 empty] | yes
| Lambourn | B4000, Ermin Street, Shefford Woodlands | Request to extend 50mph to District boundary | 2004-06-14 | The extent and current speed limit is appropriate for the length and nature of the road. The frontage development is within the existing 50mph speed limit and therefore it is not recommended to extend this limit. Investigation into improvement of road marking and signs |  |  |  | N/A
| Compton | Churn Road | Request for 30mph speed limit | 2004-06-14 | Drivers using this road are regular users and travel at an appropriate speed. Recommendation is that no further action be taken on this request. |  |  |  | N/A
| Inkpen | Rooksnest Lane / Great Common | Request for 30mph speed limit | 2004-06-14 | To be consistent with other village environments within the area it is recommended that a 30mph speed limit be introduced. |  |  |  | 2005-04-18
| Hungerford | Hungerford Common | Request for 40mph speed limit through Hungerford Common | 2004-06-14 | Considered that traffic speeds through the Common are on average between 30 and 40mph. The introduction of additional signs could be considered to be urbanising the natural environment. Recommended that no further action be taken. |  |  |  | N/A
| Hungerford | B4192, Charnham Park | Request for 40mph speed limit | 2004-06-14 | Recommend introduction of 40mph speed limit on the B4192 to link the existing 40mph speed limits on the A4 and Charnham Park, Hungerford. Also recommend to extend existing 30mph on the A4 towards the B4192 junction so the start of the 30mph speed limit is at the commencement of the frontage development on the A4. |  |  |  | 2005-05-11
| Hungerford | A338, Eddington Hill | Request to extend 30mph speed limit | 2004-06-14 | Recommend that existing 30mph speed limit be extended to give drivers travelling south on the downward gradient sufficient time to reduce their speed to an appropriate level when passing the residential frontages. |  |  |  | 2005-05-23
| Great Shefford | A338, Hungerford Hill | Request to extend 30mph speed limits on village approaches | 2004-06-14 | It is considered the current speed limit is appropriate for this length of road. Therefore it is recommended that no further action be taken. |  |  |  | N/A
| Great Shefford | Church Street | Request to extend 30mph speed limits on village approaches | 2004-06-14 | It is considered the current speed limit is appropriate for this length of road. Therefore it is recommended that no further action be taken. |  |  |  | N/A
| Great Shefford | A338 Wantage Road | Request to extend 30mph speed limits on village approaches | 2004-06-14 | It is considered the current speed limit is appropriate for this length of road. Therefore it is recommended that no further action be taken. |  |  |  | N/A
| Great Shefford | Newbury Road | Request to extend 30mph speed limits on village approaches | 2004-06-14 | It is considered the current speed limit is appropriate for this length of road. Therefore it is recommended that no further action be taken. |  |  |  | N/A
| Winterbourne | Boxford Road | Request for 30mph speed limit | 2004-06-14 | Does not meet the criteria for a 30 mph speed limit. Recommended that no further action be taken. |  |  |  | N/A
| Sulhamstead | Sulham Lane | Request for 30mph speed limit | 2004-06-14 | The nature and width of the road tends to control traffic speeds, which are considered to be in the region of 30mph. It is therefore recommended no action be taken. |  |  |  | N/A
| Speen | A4 Western Avenue | Officer recommendation for 40mph speed limit | 2004-06-14 | Recommend that the existing 30 mph speed limit from between Oxford Road and Old Bath Road/Brummell Road junction be revised to 40 mph to make it more consistent with other similar lengths of the A4. Existing 30 mph speed limit would remain from a location in the vicinity of the Garage to its existing location west of Speen Lane. This would also have the benefit of having 30mph speed limit signs for traffic turning off the A4 and entering residential roads. |  |  |  | 2005-09-06
| Streatley | Rectory Road | Request to extend 30mph speed limit up to golf course | 2004-06-14 | Given the nature of the road and that it is essentially a no through road it is recommended to take no further action at present. |  |  |  | N/A
| Streatley | A329 Wallingford Road | Officer recommendation to make the speed limit on the length of road consistent with other speed limits of a similar nature. Raise to 40mph | 2004-06-14 | Introduction of a 40mph speed limit would be appropriate for the nature of the road and would act as a buffer for traffic approaching Streatley. Would also highlight to drivers the 30mph when approaching the built up area. Measures could be introduced to improve the visibility for traffic exiting Townsend Road. It is therefore recommended that a 40mph speed limit be introduced. |  |  |  | N/A
| Aldermaston | Church Road | Request for 30mph speed limit to be extended to include the entrance to Portland House. | 2004-06-14 | It is considered the current speed limit is appropriate for this length of road. Therefore it is recommended that no further action be taken. |  |  |  | N/A
2003 Speed Limit Review | [6 empty] | yes
| Aldworth | Ashampstead Road | Request for 40mph speed limit | 2003-02-07 | No further action regarding 40mph speed limit and add to Traffic management assessment programme for investigation of improvements to signing and road markings
| Hermitage | Yattendon Road | Request to improve 30mph speed limit | 2003-02-07 | Shorten speed limit & provide new gateway feature to improve conspicuity and therefore effectiveness
| Burghfield | Clay Hill Road | Request for 30/40mph speed limit | 2003-02-07 | No further action regarding 30/40mph speed limit and add to Traffic management assessment programme for investigation of signage improvements
| Shaw | Oxford Road, Donnington | Request to modify existing 30/40mph speed limit | 2003-02-07 | No further action regarding the extending of the existing speed limit
| Shaw | B4494 Wantage Road, Donnington | Request for 30/40mph speed limit | 2003-02-07 | 40mph speed limit to be implemented from the junction with the Mini Roundabout to junction with A34 Over bridge
| Padworth | Rectory Road / Padworth Road, Padworth | Request for 40mph speed limit | 2003-02-07 | No further action regarding the 40mph sped limit and add to traffic management assessment programme for investigation of alternative measures
| Burghfield | Reading Road, Aldermaston to Burghfield | Request for 40/50mph speed limit | 2003-02-07 | Agreed 50mph speed limit from Soke Road Roundabout to existing 50mph speed limit
| Burghfield | Goring Lane, Burghfield to Grazeley Green | Request for 40/50mph speed limit | 2003-02-07 | Agreed 50mph speed limit on Goring Lane to Fullers Lane Grazeley Green
2002 Speed Limit Review | [6 empty] | yes
NO REPORTS ON FILE INDICATING TASK GROUP MET
2001 Speed Limit Review | [6 empty] | yes
| Leckhampstead | Leckhampstead Thicket | Request for 30mph speed limit | 2001-10-29 | Recommend enhancements to improve driver awareness. Does not meet criteria for 30mph speed limit. Any introduction of a limit would likely have little effect as traffic is local/regular user |  |  | completed | N/A
| Chieveley | Graces Lane | Request to extend 30mph limit to beyond motorway junctions | 2001-10-29 | Scheme to be designed for enhancement of the entry point to the limit. In discussion with Chieveley PC on additional funding from developer.
| Burghfield | Pingewood Road, North | Request for 30mph speed limit if not able to progress with stopping up | 2001-10-29 | Recommend site visit following decision on road closure
| Brightwalton | Brightwalton Green | Request for 30mph speed limit | 2001-10-29 | No changes to area since last request therefore no further action recommended
| Boxford | Coombesbury Lane | Request for 30mph speed limit | 2001-10-29 | No changes to area since last request therefore no further action recommended
| Beedon | Stanmore | Request for 30mph speed limit | 2001-10-29 | Does not meet the criteria for a 30mph speed limit. No further action recommended.
| Beedon | Westons | Request for 20mph speed limit | 2001-10-29 | Small cul-de-sac subject to 30mph. Parked vehicles will keep speeds very low, therefore no further action recommended.
| Basildon | Lower Basildon | Request to extend 30mph limit further from the Crown PH. | 2001-10-29 | Village has two speed cameras within the existing limit. Taking the limit out could have a detrimental effect on vehicle speeds. No further action recommended.
| Pangbourne | Pangbourne Hill | Request to extend 30mph limit up to junction with Pangbourne Road. | 2001-10-29 | Does not meet the criteria for a 30mph speed limit. No further action recommended.
| Aldermaston | A340 Aldermaston to Tadley (County Boundary) | Request for 50mph speed limit | 2001-10-29 | Accident record indicates a possible need for a reduction. A site visit confirmed that 50mph would be an appropriate speed and would most likely be adhered to. It was recommended to proceed with advertisement subject to approval from the Executive Committee
| Burghfield | Burghfield to Tadley Road | Request for 40mph or 50mph speed limit | 2001-10-29 | 7 PIAs in the section of road subject to 50mph limit since its introduction in March 1999. 4 of the accidents occurred in wet/icy conditions. In the three year period prior to introduction there were 8 PIAs. Proposed to investigate surface feature of the road and consider signing and lining measures to improve the accident record.
| Woolhampton | A4 east of Woolhampton | Request for 40mph limit from the Esso Garage up to the junction with Frouds Lane | 2001-10-29 | A4 is a wide road with few properties fronting the carriageway and a 40mph speed limit is unlikely to be adhered. No further action recommended.
| Aldermaston | Frouds Lane | Request for 40mph speed limit | 2001-10-29 | Does not meet the criteria for a 40mph speed limit. No further action recommended.
| Aldermaston | Wasing Lane | Request for 40mph speed limit | 2001-10-29 | Does not meet the criteria for a 40mph speed limit. No further action recommended.
| Inkpen | Rooksnest Lane, Inkpen Common | Request for 30mph speed limit | 2001-10-29 | Does not meet the criteria for a 30mph speed limit. No further action recommended.
| Brimpton | Brimpton Lane | Request for 30mph or 40mph speed limit | 2001-10-29 | Recommend introduction of 40mph speed limit to a point just north of Back Lane only as remaining length does not meet the criteria for 40mph or 30mph limit
| Padworth | Padworth Lane and Rectory Road | Request for a 20-30mph speed limit | 2001-10-29 | Roads are not street lit and therefore do not meet the criteria for a 20mph limit. Does not meet the criteria for a 30mph speed limit. No further action recommended.
| Padworth | Welshmans Road | Request for a reduction in the speed limit | 2001-10-29 | Only very short length of the road is in West Berkshire. If Hampshire introduced a speed limit there would be no objection to extending it to the junction
| Newbury | A343 Andover Road | Request to extend 40mph limit at southern end of Andover Road and reduce existing 40mph limit to 30mph | 2001-10-29 | Vehicle speeds unlikely to be effected by amendments to limit without traffic calming measures. Problems may be as a result of poor visibility at the junction with Washwater. Investigate measures to address road safety at the junction.
| Great Shefford | Great Shefford | Request for extensions to existing speed limit | 2001-10-29 | Existing limits are set at their optimum distance. Recommend to investigate possible treatments to enhance existing limit
|  | B4494 |  | 2001-10-29 | Recommend to review accident information and review measures to improve driver awareness of hazards
| Newbury/Speen | A4 Bath Road | Request to increase 30mph speed limit from Brummel Road to College Roundabout. | 2001-10-29 | Correspondence from GOSE suggest that 40mph is an inappropriate speed for this length of road. Task Group to consider further
2000 Speed Limit Review | [6 empty] | yes
| Newbury | Andover Road | To extend 30/40mph speed limit | 2000-09-29 | No change to speed limit. Investigate resiting speed camera
|  | B4494 Wantage Road | Extend 30mph speed limit Implement 40mph speed limit | 2000-09-29 | No Action. Difficult to sign a limit due to the nature of the road.
| Newbury | Monks Lane | Reduce 40mph speed limit to 30mph | 2000-09-29 | Agreed to reduce limit to 30mph Consider reduction of speed limit on A339 to 50mph prior to detrunking.
| Newbury | Wheatlands Avenue | Request for 30mph speed limit | 2000-09-29 | No Action, does not meet the criteria for a 30mph speed limit.
|  | Coombesbury Road,Wickham Heath | Request for speed limit along its length | 2000-09-29 | Does not meet the criteria for a 30/40. To approach Parish Council for Possible justification of request
| Basildon | Mead Lane, U Basildon | Request for 30mph speed Limit | 2000-09-29 | No action recommended. Does not meet the criteria.
| Basildon | Park Wall Lane, U Basildon | Request to extend 30mph speed limit | 2000-09-29 | No action recommended. Does not meet the criteria.
| Basildon | Pangbourne Road, U Basildon | Request to extend 30mph speed limit | 2000-09-29 | No action recommended. Does not meet the criteria.
| Brimpton | Crookham Road, Brimpton | Request for 30mph speed Limit | 2000-09-29 | Agreed to extend 40mph speed limit to Travellers Rest PH
| Bucklebury | Chapel Row, Bucklebury Road leading to Hillfoot | Request to extend 30mph speed limit beyond housing through Hillfoot | 2000-09-29 | The route does not meet the criteria for a speed limit, recommended to carry out an assessment of the signage.
| Burghfield | Pingewood Road, North | Police advised there is a system of street lighting o/s Cunning Man PH And therefore should either be a 30mph speed limit or a traffic order produced for the national speed limit. | 2000-09-29 | Agreed to include in Pingewood Road closure report to T-Sub,
| Burghfield | Clayhill Road | Request for 30mph speed limit | 2000-09-29 | Does not meet criteria, therefore No action recommended
| Calcot | A4 Bath Road | Request to extend 40mph speed Limit to District Boundary | 2000-09-29 | Agreed to extend 40mph speed limit And inform RBC.
|  | B4494, Lilley | Request for 40mph speed limit | 2000-09-29 | Does not meet the criteria for a speed limit. Recommended to introduce advisory speed limit signs on bend.
|  | Goring Lane, Grazeley Green | Request for 30/40mph speed limit | 2000-09-29 | Does not meet criteria, therefore No action recommended
|  | Post Office Road, Inkpen | Request to extend limit to cover housing development | 2000-09-29 | Agreed to extend limit to cover Upper Green.
|  | Inkpen Common | Request for 30mph speed limit | 2000-09-29 | Does not meet criteria, therefore No action recommended
|  | Leckhampstead Thicket | Request for 20/30mph speed limit | 2000-09-29 | To ascertain extent of the problem it is recommended to carry out a speed survey and report the findings to a future meeting of the Transportation Sub-Committee
|  | B4494 / Egypt crossroads | Request to extend 30mph limit to Junction | 2000-09-29 | The entry to the limit was located at its present position as it is not physically possible to site the signs at the junction.
|  | B4494 | Request to extend 50mph limit From Brightwalton Holt south to Chapel Arch | 2000-09-29 | A 50mph speed limit can not be justified along this length, however it was agreed to introduce secondary speed markings at the Egypt crossroads in an attempt to reduce vehicle speeds, as it meets the TVP criteria.
|  | South Fawley | Request for 30mph speed limit | 2000-09-29 | Vehicle speeds are kept through the nature of the roads through the village. To improve driver awareness it is recommended to improve the village nameplate and include the ‘Please Drive Slowly through village’
| Tidmarsh and Sulham | Sulham Lane | Request for 30mph speed limit | 2000-09-29 | The route does not meet the criteria for a speed limit. It is recommended to review the signing along the route with the view to improve road safety.
| Mortimer | The Street | Request to reduce speed limit from 40mph to 30mph. | 2000-09-29 | Does not meet the criteria for a 30mph speed limit. No further action recommended.
| Lambourn | Hungerford Hill / Baydon Road | Request for traffic calming measures | 2000-09-29 | The police traffic surveys indicate 85th%ile speeds of between 28 and 34 mph on Baydon Road, which would not justify The implementation of traffic calming Measures. Similar speeds would be expected on Hungerford Hill. Funding to improve gateway features.